## AgriCiv Risk Register
AGRICIV SAMPLE RISK REGISTER
RISK ID | RISK DESCRIPTION | ASSET/PROCESS AFFECTED | LIKELIHOOD (1-5) | IMPACT (1-5) | RISK LEVEL | MITIGATION NOTES | OWNER | STATUS | KEY
R-001 | Over-reliance on founder for daily operations | Operational Continuity | 5 | 5 | 25 | Develop succession plan and SOPs for core processes | Head of Operations | In Progress | 1 | VERY LOW
R-002 | Data loss during transition to cloud-based systems | Data Storage & Records | 3 | 4 | 12 | Implement regular backups and phased migration plan | IT Lead | In Progress | 2 | LOW
R-003 | Cybersecurity threat from weak access controls on Zoho ERP | ERP System & Access Control | 4 | 5 | 20 | Enforce MFA and least privilege access policies | IT Security Lead | Not Started | 3 | MODERATE
R-004 | Low turnover of high-value inventory leading to cash flow strain and equipment depreciation | Sales Strategy & Financial Liquidity | 3 | 5 | 15 | Introduce rental options for selected equipment, diversify revenue through after-sale services, and track stock ageing quarterly | Sales Manager | Complete | 4 | HIGH
R-005 | Delays in equipment shipments due to foreign supply chain disruptions | Procurement & Logistics | 3 | 4 | 12 | Diversify suppliers and build local stock buffer | Procurement Officer | Not Started | 5 | VERY HIGH
R-006 | Lack of documented policies for employee roles and responsibilities | Human Resources | 5 | 3 | 15 | Define roles in employee handbook and training plans | HR Manager | In Progress
R-007 | Unreliable power supply due to potential ZESA outages | Physical Environment & Business Continuity | 1 | 5 | 5 | Install solar panels and inverter for backup power in case of outages | Facilities Manager | Not Started
R-008 | Primary Wi-Fi connectivity issues disrupting cloud-based operations | IT Infrastructure & Communications | 4 | 4 | 16 | Purchase and maintain a mobile internet dongle with 100GB monthly data as backup | IT Lead | In Progress
R-009 | Limited internal knowledge of Zoho ERP functionality due to recent implementation | Change Management & Training | 4 | 4 | 16 | Mr. F is training the newly hired admin assistant to use Zoho ERP and optimise workflows; she will later train others | Operations Manager | In Progress
R-010 | Incomplete data migration leading to operational disruptions | Data Integrity & ERP Implementation | 3 | 5 | 15 | Conduct staged migration with regular data quality checks and backups | ERP Project Manager | In Progress
R-011 | Fluctuating local currency (RTGS) impacting consistency in payments and pricing | Financial Transactions & Revenue Management | 4 | 4 | 16 | Standardise transactions in USD through cash, EcoCash, and bank transfers; align supplier payments to USD | Finance Manager | Ongoing
R-012 | Loss of key supplier relationships due to informal contract agreements | Vendor & Procurement Management | 3 | 4 | 12 | Formalise supplier agreements and introduce basic vendor SLAs | Procurement Officer | In Progress

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T